## Simple Business Risk Register
RISK REGISTER
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
*Extension - Google Maps API may be down/buggy | External API, difficult to manage issues and minimise for users | 3 | 2 | 6 | Error handling to inform users API is down | Capstone team | 1
Errors/incomplete data updates could create bugs when viewing profiles/booked holiday | Users may not be able to update their address (out of date, security issues) / holiday is not requested | 4 | 2 | 8 | Incorporate atomic transactions to ensure any data updates are processed | Capstone team | 2
Security - accessed by employees or those outside the company | Personal/sensitive details can be accessed without required rights | 5 | 2 | 10 | Ensure user access rights are accurate & up to date, setup error handling if users attempt to access data outside of their role | Capstone team | 3
Server performance | Users (satisfactory) delays to booking holiday, updating personal details | 2 | 2 | 4 | Offline message - dev team are working to restore, will be notified when system is back online | Capstone team
Server performance/downtime | Admin (productivity), affecting payroll processing, employee onboarding, access slow/offline | 4 | 2 | 8 | Offline message - dev team are working to restore, will be notified when system is back online. Maintenance to be completed during off peak hours | Capstone team | 4
5

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.